## Slide 1: Cost Estimation

## Slide 2: Cost Estimation
Model proposed by B. W. Boehm’s through his book Software Engineering Economics in 1981
The Constructive Cost Model (COCOMO)
Constructive Cost model (COCOMO)
Detailed
Basic
Intermediate

## Slide 3: Cost Estimation
COCOMO applied in
Semidetached mode
Embedded mode
Organic mode
COCOMO

## Slide 4
The comparison of three COCOMO modes

## Slide 5: Cost Estimation
Basic Model
Basic COCOMO model takes the form
where E is effort applied in Person-Months, and D is the development time in months. The coefficients ab, bb, cb and db are given in table 4.

## Slide 6: Cost Estimation
Table 4: Basic COCOMO coefficients

## Slide 7: Cost Estimation
When effort and development time are known, the average staff size to complete the project may be calculated as:
When project size is known, the productivity level may be calculated as:

## Slide 8: Cost Estimation
Example
Suppose that a project was estimated to be 400 KLOC. Calculate the effort and development time for each of the three modes i.e., organic, semidetached and embedded.

## Slide 9: Cost Estimation
Solution
The basic COCOMO equation take the form:
Estimated size of the project = 400 KLOC
(i) Organic mode
E = 2.4(400)1.05 = 1295.31 PM
D = 2.5(1295.31)0.38 = 38.07 M

## Slide 10: Cost Estimation
Semidetached mode
E = 3.0(400)1.12 = 2462.79 PM
D = 2.5(2462.79)0.35 = 38.45 M
Embedded mode
E = 3.6(400)1.20 = 4772.81 PM
D = 2.5(4772.8)0.32 = 38 M

## Slide 11: Cost Estimation
Example:
A project size of 200 KLOC is to be developed. Software
development team has average experience on similar type of
projects. The project schedule is not very tight. Calculate the effort, development time, average staff size and productivity of the project.

## Slide 12: Cost Estimation
The semi-detached mode is the most appropriate mode; keeping in view the size, schedule and experience of the development team.

## Slide 13: Cost Estimation

## Slide 14: Cost Estimation
Intermediate Model
Product Attributes
  Required s/w reliability (RELY)
  Size of application database (DATA)
  Complexity of the product (CPLX)
  (ii) Hardware Attributes
  Run time performance constraints (TIME)
  Memory constraints (STORE)
  Virtual machine volatility (VIRT)
  Turnaround time (TURN)
Cost drivers

## Slide 15: Cost Estimation
Personal Attributes
  Analyst capability
  Programmer capability
  Application experience
  Virtual m/c experience
  Programming language experience
Project Attributes
  Modern programming practices ()
  Use of software tools
  Required development Schedule

## Slide 16: Cost Estimation
Multipliers of different cost drivers

## Slide 17: Cost Estimation
Multipliers of different cost drivers

## Slide 18: Cost Estimation
Project | ai | bi | ci | di
Organic | 3.2 | 1.05 | 2.5 | 0.38
Semidetached | 3.0 | 1.12 | 2.5 | 0.35
Embedded | 2.8 | 1.20 | 2.5 | 0.32
Coefficients for intermediate COCOMO
Intermediate COCOMO equations
The multiplying factors for all 15 cost drivers are multiplied to get the effort adjustment factor (EAF)