## Slide 1: Software Risk Management

## Slide 2: Software Risk Management
Software Risk Management
We Software developers are extremely optimists.
We assume, everything will go exactly as planned.
Other view
not possible to predict what is going to happen ?
Software surprises Never good news

## Slide 3: Software Risk Management
management is required to reduce this surprise
Risk factor
Dealing with concern before it becomes a crisis.
Quantify probability of failure & consequences of failure.

## Slide 4: Software Risk Management
What is risk ?
Tomorrow’s problems are today’s risks.
“Risk is a problem that may cause some loss or threaten the success of the project, but which has not happened yet”.

## Slide 5: Software Risk Management
Risk management is the process of identifying, addressing and eliminating these problems before they can damage the project.
Current problems &
Potential Problems

## Slide 6: Software Risk Management
Typical Software Risk
Capers Jones has identified the top five risk factors that threaten projects in different applications.
Dependencies on outside agencies or factors.
  Availability of trained, experienced persons
  Inter group dependencies
  Customer-Furnished items or information
  Internal & external subcontractor relationships

## Slide 7: Software Risk Management
2.
Requirement issues
Uncertain requirements
Wrong product
or
Right product badly
Either situation results in unpleasant surprises and unhappy customers.

## Slide 8: Software Risk Management
Lack of clear product vision
Lack of agreement on product requirements
Unprioritized requirements
New market with uncertain needs
Rapidly changing requirements
Inadequate Impact analysis of requirements changes

## Slide 9: Software Risk Management
3. Management Issues
Project managers plans, and most
usually write the risk management people do not wish to air their
weaknesses in public.
Inadequate planning
Inadequate visibility into actual project status
Unclear project ownership and decision making
Staff personality conflicts
Unrealistic expectation
Poor communication

## Slide 10: Software Risk Management
4.
Lack of knowledge
Inadequate training
Poor understanding of methods, tools, and techniques
Inadequate application domain experience
documented or neglected
New Technologies
Ineffective, poorly processes

## Slide 11: Software Risk Management
5.
Other risk categories
Unavailability of adequate testing facilities
Turnover of essential personnel
Unachievable performance requirements
Technical approaches that may not work

## Slide 12: Software Risk Management
Risk Management
Risk Assessment
Risk Control
Risk Identification
Risk Analysis
Risk Prioritization
Risk Management Planning
Risk Monitoring
Risk Resolution
Risk Management Activities
Fig. 9: Risk Management Activities

## Slide 13: Software Risk Management
Risk Assessment
Identification of risks
Risk analysis involves examining how project outcomes might change with modification of risk input variables.
Risk prioritization focus for severe risks.
Risk exposure: It is the product of the probability of incurring a loss due to the risk and the potential magnitude of that loss.

## Slide 14: Software Risk Management
Another way of handling risk is the risk avoidance. Do not do the risky things! We may avoid risks by not undertaking certain projects, or by relying on proven rather than cutting edge technologies.

## Slide 15: Software Risk Management
Risk Control
Risk Management Planning produces a plan for dealing with each significant risks.
Record decision in the plan.
Risk resolution is the execution of the plans of dealing with each risk.